## Sheet1
Task | Description | status | Developer Name
Working Schemes
Medhavi putra/putri scheme |  | InProgress | Rashmi
Completed schemes
Jharkhand Nirman Karmkar Mrithyu/Durghatna Sahayata Yojana
Anath Pension Yojana
Nihshaktata Pension Yojana
Parivar Pension Yojana
Antyesti Sahayata Yojana
Chikitsa Pratiputri Yojana
Chikitsa Sahayata Yojana
Pending schemes
Shramik Auzar Sahayata Yojana
Cycle Sahayata Yojana
Saraswati Yojana
Nirman Shramik Safety Kit Yojna
Pension Yojana
Vivah Sahayata Yojana
Matritva Prasuvidha Yojana
Other Pending Items:
Final UI/UX adjustments for homepage and dashboard
Aadhaar-based login (pending client inputs)
Bank account validation via Aadhaar (pending client inputs)
SBI ePay integration (Initial implementation was done using Razorpay; SBI ePay to be integrated as per new requirement)
Admin Dashboard listing by scheduler
Bugs Lists
Satyam
BF > Applied Scheme > Breadcrumbs (Dashboard > List) | Breadcrumb navigation is not working correctly | Done
BF > Applied Scheme > Switch to Dashboard: | Menu navigation issue occurs when switching between dashboards. | Done
Menu Issues: | Only two menus are visible: View Dashboard and Active Scheme.
Some menus are missing (specific to LS site).
This is a client-side issue.
LS > Beneficiaries Scheme Application > View > Upload your files here: | Upload button is not working. | Its not an issue
BF > Applied Scheme > User > Edit: | Forms are submitted, but edit and submit options are still showing.
Clicking the edit button allows data changes and resubmission.
This leads to unintended data changes post-submission.
BF > BF Beneficiaries Scheme Application > View > Antyeshti Sahayata Yojana > Dependent D.O.B: | D.O.B accepts future dates – needs validation to restrict future dates.
BF > Applied Scheme > View List > View > Schemes Application Form: | Menu navigation issue.
BF > Applied Scheme > Scheme Name | Dropdown list is not loading alphabetically.
Autocomplete not working properly.
BF > Applied Scheme > Scheme Applied Application Status | Status not showing (e.g., Pending).
Affects beneficiaries scheme listing.
LS > Scheme Title > Scheme Dropdown Menu | Dropdown not showing.
Scheme listing missing.
LS > Beneficiaries Scheme Application | Age sorting not working
BF > Grievances > Scheme Name | Dropdown menu not working.
Scheme names are not displaying.